## Schedule
Parametric APDL Horizontal Tailplane Structural Analysis |  | Total Tasks | Completed | In Progress | Pending | Proposal Milestone
Project Schedule & Milestone Tracking |  | 10 | 3 | 1 | 6 | 2026-09-30
Task ID | Task Name | Category / Deliverable | Status | Start Date | End Date | Duration (Days)
T-01 | Initial topic study (aircraft window structure) | Topic Selection & Literature | Completed | 2026-09-16 | 2026-09-22 | 7
T-02 | Topic change to horizontal tailplane; literature review | Topic Selection & Literature | Completed | 2026-09-23 | 2026-09-25 | 3
T-03 | Step 1: Data collection & parameter definition | Stage 1: Input Data | Completed | 2026-09-26 | 2026-09-27 | 2
T-04 | Step 2: Parametric APDL script development | Stage 2a: APDL Script | In Progress | 2026-09-28 | 2026-09-30 | 3
T-05 | Proposal presentation for project approval | Major Milestone | Pending | 2026-09-30 | 2026-09-30 | 1
T-06 | Step 3: SFBM load pre-processing (MATLAB) | Stage 2b: Load Reconstruction | Pending | 2026-10-01 | 2026-10-02 | 2
T-07 | Step 4: Configuration setup & Step 5: Model verification | Stage 3a-b: Setup & Verification | Pending | 2026-10-03 | 2026-10-04 | 2
T-08 | Step 6: Static analysis & Step 7: Baseline validation | Stage 3c: Static FEM Analysis | Pending | 2026-10-05 | 2026-10-06 | 2
T-09 | Step 8: Evaluation & comparison (Config A, B, C) | Stage 3d: Optimization | Pending | 2026-10-07 | 2026-10-08 | 2
T-10 | Step 9: Final Report preparation | Documentation & Submission | Pending | 2026-10-09 | 2026-10-10 | 2
Total | [5 empty] | 26

## Gantt Chart
Horizontal Tailplane Project Timeline (Gantt Chart)
Visual Project Workflow ¦ Aerospace Structural Optimization
Task ID | Task Name | Status | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10
T-01 | Initial topic study (aircraft window structure) | Completed | █ | █ | █ | █ | █ | █ | █
T-02 | Topic change to horizontal tailplane; literature review | Completed | [7 empty] | █ | █ | █
T-03 | Step 1: Data collection & parameter definition | Completed | [10 empty] | █ | █
T-04 | Step 2: Parametric APDL script development | In Progress | [12 empty] | █ | █ | █
T-05 | Proposal presentation for project approval | Pending | [14 empty] | ◆
T-06 | Step 3: SFBM load pre-processing (MATLAB) | Pending | [15 empty] | █ | █
T-07 | Step 4: Configuration setup & Step 5: Model verification | Pending | [17 empty] | █ | █
T-08 | Step 6: Static analysis & Step 7: Baseline validation | Pending | [19 empty] | █ | █
T-09 | Step 8: Evaluation & comparison (Config A, B, C) | Pending | [21 empty] | █ | █
T-10 | Step 9: Final Report preparation | Pending | [23 empty] | █ | █

## Budget
Estimated Project Budget & Resource Allocation |  | Total Allocated Budget | Total Actual Cost | Net Variance
Coursework & Laboratory Resource Utilization ¦ APDL & MATLAB |  | 0 | 0 | 0
Item / Resource | Description | Source & Licensing | Cost (THB) | Funding Status
ANSYS Mechanical APDL 2026 R1 | Finite element modelling and structural analysis | ANSYS Student version (free) | 0 | University / Academic Free
MATLAB | SFBM load pre-processing & numerical solver | University license (student academic account) | 0 | Institutional License
Computer workstations | Running simulations and mesh generation | Personal student laptops | 0 | Existing Personal Resource
Course materials & reports | Documentation and presentation materials | Digital submission | 0 | Department Digital Facility
Total Estimated Cost |  |  | 0 | Fully Funded / Zero Cost